## AUEU Proposal WorklPlan
Name of Organisation: | Geoanaltech
Country: | Nigeria
Project Name: | Empower and enhance the wellbeing of young people with disabilities including intellectual disabilities, between the ages of 15-35 years by providing access to in-demand technology skills, fostering inclusive communities through awareness, research, advocacy, and promoting safe spaces in Kano State.
Project Period: | 15 months
OBJECTIVES | ACTIVITIES | PERSONS RESPONSIBLE | TIMELINE
|  |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01
Objective 1. Significantly empower young people with disabilities, including intellectual disabilities, between the ages of 15-35 years by equipping them with in-demand technology skills such as data analytics, web development, and geographic information systems through targeted training programs tailored to meet the specific needs of participants. | 1.Needs assessment for tech training enrolment of youth between 15-35 living with disabilities including people living with intellectual disabilities. | Monitoring, Evaluation and Learning Officer | bar: 2025-05-01 to 2025-06-01
| 2.Dialogue with stakeholders at the local levels to understand the existing programs supporting people living with disabilities. | Programme Manager | bar: 2025-05-01 to 2026-05-01
| 3.Identify facilitators, government structures including schools, policymakers, non-governmental organisations, and Organizations of Persons with Disabilities (OPDs) in Kano State that promote disability inclusion | Programme Management Team | bar: 2025-05-01 to 2025-06-01
| 4.Train young people with disabilities on in-demand technology skills | Facilitators | bar: 2025-07-01 to 2026-07-01
| 5. Curriculum development for tailored courses | Training Coordinator | bar: 2025-05-01 to 2025-06-01
| 6. Pre-test for participants | Facilitators | bar: 2025-07-01
| 7. Post-test for participants | Facilitators | bar: 2026-07-01
Objective 2. Create public awareness for effective social inclusion for people with intellectual disabilities | 1.Organize community dialogues with leaders, parents and caregivers on the importance of disability inclusion. | Program Officer/ Program Manager | bar: 2025-07-01 to 2026-07-01
| 2.Facilitate policy dialogues with local government councils to promote equal opportunities for persons with disability and their rights to services including education, health, employment etc | Program Manager | bar: 2025-07-01 to 2026-07-01
| 3.Foster collaborations and build partnerships with government institutions, development partners, Civil society Organizations, Organizations of Persons with Disabilities (OPDs), National Commission for Persons with Disabilities (NCPWD) to promote the | Program Manager | bar: 2025-07-01 to 2026-07-01
Objective 3. Provide grant research into prevalence of intellectual disabilities in communities in Kano (various disabilities) | 1. Rapid survey to identify the number of people with intellectual disabilities in communities in Kano. | Program Officer/ Monitoring, Evaluation and Learning Officer | bar: 2025-05-01 to 2025-06-01
| 2. Engage with organizations of persons with disabilities for review of existing database on persons with mental disabilities | Monitoring, Evaluation and Learning Officer | bar: 2025-05-01 to 2025-06-01
| 3. Research protocol and methodology development | Program Mangement Team | bar: 2025-05-01 to 2025-06-01
| 4. Data Collection (Rapid Survey) | Monitoring, Evaluation and Learning Officer | bar: 2025-07-01
| 5. Data Analysis & Report Writing | Monitoring, Evaluation and Learning Officer | bar: 2025-08-01
| 6. Dissemination of Research Findings | Program Mangement Team | bar: 2025-08-01
Objective 4. Create a safe environment for young people with intellectual disabilities | 1. Organize community inclusive events/support groups for peer-to-peer interaction, and caregivers’ forum | Program Officer | bar: 2025-07-01 to 2026-07-01
| 2. Mapping of and referral to available psychosocial support services | Program Officer | bar: 2025-05-01 to 2025-06-01
| 3. Community awareness creation on available support services | Program Management Team | bar: 2025-07-01 to 2026-07-01
Monitoring & Evaluation (Cross cutting) | 1. Inception report | Monitoring, Evaluation and Learning Officer/ Program Manager | bar: 2025-05-01 to 2025-06-01
2. Progess reports | bar: 2025-07-01 to 2026-07-01
| 3. Evaluation reports (Mid-term and Endline evaluation) | Consultant | bar: 2026-01-01; 2026-08-01
| 4. Data Management System | Monitoring, Evaluation and Learning Officer | bar: 2025-07-01 to 2026-07-01
| 5. Data Analysis, Reporting, Dashboard Development | Monitoring, Evaluation and Learning Officer/ Program Manager | bar: 2025-07-01 to 2026-07-01
WORKPLAN SHOWING CLEARLY ACTIVITIES AND TIMELINE FOR EACH
Goal: To significantly improve the employability and enhance the wellbeing of young people with disabilities, including intellectual disabilities, between the ages of 15-35 years by providing access to in-demand technology
skills, fostering inclusive communities through awareness, research, advocacy, and promoting safe spaces in Kano State over 15 months.